## Projects
Project ID | Project Name | Start Date | End Date | Project Manager | Status | Budget ($)
P001 | Website Redesign | 2025-06-01 | 2025-07-15 | Alice Johnson | In Progress | 10000
P002 | Mobile App Launch | 2025-06-10 | 2025-08-30 | Mark Benson | Not Started | 20000
P003 | Data Migration | 2025-05-01 | 2025-06-30 | Sarah Lee | Completed | 15000
P004 | CRM Implementation | 2025-07-01 | 2025-09-30 | David Kim | Not Started | 25000

## Tasks
Task ID | Task Name | Project ID | Assigned To | Start Date | End Date | Status | % Complete
T001 | UI Design | P001 | John | 2025-06-01 | 2025-06-10 | Completed | 100
T002 | Backend Integration | P001 | Priya | 2025-06-05 | 2025-06-20 | In Progress | 60
T003 | Testing | P001 | Ravi | 2025-06-21 | 2025-07-10 | Not Started | 0
T004 | Planning | P002 | Alex | 2025-06-10 | 2025-06-20 | Not Started | 0
T005 | Data Backup | P003 | Nina | 2025-05-01 | 2025-05-10 | Completed | 100
T006 | Migration Script | P003 | Jason | 2025-05-11 | 2025-06-15 | Completed | 100
T007 | Requirement Gathering | P004 | Emily | 2025-07-01 | 2025-07-10 | Not Started | 0
T008 | Vendor Selection | P004 | Liam | 2025-07-10 | 2025-07-20 | Not Started | 0